## Project Planner
Project Title
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Define the project requirements | 1 | 1 | 1 | 1 | 100%
2. Identify and meet with stakeholders | 2 | 1 | 2 | 1 | 100%
3. Develop program charter | 3 | 1 | 3 | 1 | 0%
4. Collect requirements | 4 | 1 | 4 | 1 | 0%
5. Define scope | 5 | 1 | 5 | 1 | 100%
6. Create WBS | 6 | 1 | 6 | 1 | 100%
7. Define activities | 7 | 1 | 6 | 1 | 100%
8. Sequence activities | 7 | 1 | 6 | 1 | 100%
9. Estimate activities duration | 8 | 1 | 6 | 1 | 50%
10. Identify and estimate resource requirements | 9 | 1 |  |  | 0%
11. Consider resource availability and risks | 10 | 2 |  |  | 0%
12. Acquire project team | 12 | 1 |  |  | 0%
13. Assign tasks | 13 | 2 |  |  | 0%
14. User Interface Design | 15 | 5 |  |  | 0%
15. System Design | 20 | 5 |  |  | 0%
16. Coding | 25 | 25 |  |  | 0%
17. Testing | 50 | 3 |  |  | 0%
18. Deployment | 53 | 2 |  |  | 0%
19. Manage communication | 7 | 48 |  |  | 0%
20. Update project plan | 7 | 48 |  |  | 0%
21. Performance quality assurance | 25 | 30 |  |  | 0%
22. Manage changes | 7 | 48 |  |  | 0%
23. Control the cost, timeframe of the project | 7 | 48 |  |  | 0%
24. Control quality, scope and resources | 7 | 48 |  |  | 0%
25. Monitor risks | 7 | 48 |  |  | 0%
26. Close project | 55 | 3 |  |  | 0%
27. Close procurement | 58 | 3 |  |  | 0%